## Form responses 1
Timestamp | Who are you? | How many hours? | Description | Gantt Chart Task Name | When?
2017-02-27 18:23 | Romain Nith | 4 | Preliminary hardware draft design/test for shooting mechanism. Ideas for defense, no implementation yet |  | 2017-02-27
2017-03-03 17:59 | Romain Nith | 2 | Hardware/Software meeting |  | 2017-03-01 | There is a Global Time Log Sheet below for all other hours per team member + overtime
2017-03-27 21:15 | Julien Courbebaisse | 4 | new localization testing and implementation | software development | 2017-03-25
2017-03-04 23:48 | Nayem Alam | 1 | Gannt Chart fix |  | 2017-03-02
2017-03-06 11:48 | Meeting (Whole Team) | 1 | Meeting |  | 2017-03-06
2017-03-04 23:49 | Nayem Alam | 1 | Gannt Chart Edit | workload | 2017-03-04
2017-03-07 12:36 | Ali Sharif | 1 | Performed testing with catapult to determine optimal swing time and arm length. |  | 2017-03-06
2017-03-07 12:37 | Philippe Papineau | 1 | Performed testing with catapult to determine optimal swing time and arm length. |  | 2017-03-06
2017-03-07 12:40 | Ali Sharif | 1 | Performed experiments to determine which motor class would be better for use with the catapult launcher. |  | 2017-03-01
2017-03-07 12:40 | Romain Nith | 1 | Hardware documentation |  | 2017-03-07
2017-03-07 12:42 | Ali Sharif | 1 | Prepared the experiment and test reports in latex |  | 2017-03-06
2017-03-07 15:53 | Meeting (Whole Team) | 1 | Meeting |  | 2017-03-07
2017-03-07 15:55 | Rami Djema | 1 | Worked on planning the way we will code the modules |  | 2017-02-07
2017-03-07 15:35 | Julien Courbebaisse | 2 | Coding + experimenting with Wifi connection |  | 2017-03-06
2017-03-07 15:35 | Julien Courbebaisse | 1 | updated + completed class diagram |  | 2017-03-06
2017-03-12 16:03 | Ali Sharif | 7 | Worked on test chassis bot. Developed sensor framework and fixed bugs in software api (Odometry Correction, Odometer, Navigator, Obstacle Avoidance, Sensor Framework) | software architecture | 2017-03-11
2017-03-13 11:04 | Meeting (Whole Team) | 1 | group meeting | management | 2017-03-13
2017-03-13 17:12 | Philippe Papineau, Ali Sharif | 2 | redesigning robot and verification | verify every aspect of design | 2017-03-13
2017-03-13 17:13 | Julien Courbebaisse, Rami Djema, Nayem Alam, Romain Nith | 1 | redesigning robot and verification | verify every aspect of design | 2017-03-13
2017-03-12 17:22 | Ali Sharif | 2 | testing docs | testing plan development | 2017-03-12
2017-03-07 00:16 | Nayem Alam | 2 | Powerpoint slides, edit docs, create new files | presentation docs | 2017-03-06
2017-03-13 19:21 | Julien Courbebaisse | 3 | working on navigation code |  | 2017-03-13
2017-03-13 17:32 | Nayem Alam | 2 | fixing up gantt chart | project management wk3 | 2017-03-13
2017-03-13 22:47 | Nayem Alam | 2 | Editing and fixing up the 4 docs | documentation | 2017-03-13
2017-03-15 11:32 | Romain Nith | 3 | Meeting with TA + Investigate Ball launcher (motorized wheel + crossbow) |  | 2017-03-14
2017-03-15 14:30 | Romain Nith | 2 | Hardware Documentation |  | 2017-03-15
2017-03-18 17:35 | Romain Nith | 5 | Designing Crossbow's Main Mechanics |  | 2017-03-17
2017-03-18 17:36 | Romain Nith | 5 | Refining and Implementing Crossbow to Chassis with Reloading in Mind |  | 2017-03-18
2017-03-19 16:56 | Romain Nith | 4 | Refining Crossbow Reload and Firing Mechanism (cont'd) |  | 2017-03-19
2017-03-14 12:02 | Nayem Alam | 3 | Updated Gantt Chart + Finished making, updating and editing presentation slides | project management wk3 | 2017-03-14
2017-03-21 14:46 | Rami Djema | 9 | Software planning and architecture |  | 2017-03-18
2017-03-21 15:32 | Meeting (Whole Team) | 1 | Worked on software codes, all docs, presentation slides, todo lists, test entries | team meeting wk4 | 2017-03-21
2017-03-21 16:12 | Philippe Papineau | 9 | Documentation, helping Romain with the crossbow mechanism |  | 2017-03-19
2017-03-21 16:13 | Philippe Papineau | 4 | Testing the catapult and working on a new chassis |  | 2017-03-10
2017-03-21 16:15 | Philippe Papineau | 5 | Documentation: Hardware docs, testing docs |  | 2017-03-19
2017-03-21 22:28 | Ali Sharif | 4 | testing of mechanical design | testing of mechanical design | 2017-03-21
2017-03-22 11:38 | Ali Sharif, Julien Courbebaisse, Rami Djema | 2 | we got values for localization and tested the robots for it's codes | initial testing of robot for the demo | 2017-03-21
2017-03-20 22:30 | Nayem Alam | 1 | Gantt chart + presentation files + additional files edited and updated | project management wk4 | 2017-03-20
2017-03-24 10:51 | Philippe Papineau, Nayem Alam | 1 | Team meeting | team meeting wk4 | 2017-03-24
2017-03-25 02:06 | Romain Nith | 5 | Post Demo Fix and Automation of Launching Mechanism + Reloading Prototyp |  | 2017-03-24
2017-03-25 15:19 | Philippe Papineau | 3 | Documentation |  | 2017-03-20
2017-03-25 15:30 | Philippe Papineau | 6 | Documentation, poster design |  | 2017-03-25
2017-03-26 14:14 | Ali Sharif | 7 | Got the wifi working for the robot. Prepared for the demo. |  | 2017-03-23
2017-03-26 14:15 | Ali Sharif | 9 | Worked on the navigation, pathfinder, and localization. |  | 2017-03-24
2017-03-22 11:42 | Nayem Alam | 1 | fixed up gantt chart, and time sheets | project management wk4 | 2017-03-22
2017-03-27 11:16 | Philippe Papineau, Nayem Alam | 1 | team meeting | team meeting wk5 | 2017-03-27
2017-03-27 21:14 | Julien Courbebaisse | 7 | demo preparation, implementation and testing of wifi, localization, shooter,navigation | software development | 2017-03-23
2017-03-27 01:29 | Nayem Alam | 2 | Poster design, preliminary design on photoshop | poster design | 2017-03-26
2017-03-27 21:28 | Nayem Alam | 1 | reviewing all the documents to make sure they're up to date | revise and edit documents | 2017-03-27
2017-03-27 22:24 | Nayem Alam | 2 | worked on gantt chart, and presentation slides | project management wk5 | 2017-03-27
2017-03-27 23:27 | Romain Nith | 6 | Reload/Ball Retrieval Design + Documentation |  | 2017-03-27
2017-03-28 15:45 | Rami Djema | 7 | testing the robot + revising the code |  | 2017-03-23
2017-03-28 15:48 | Rami Djema | 6 | review of software codes | review of software codes | 2017-03-27
2017-03-28 16:11 | Julien Courbebaisse | 2 | finished writing up localization test and helped with preparation of demo |  | 2017-03-28
2017-03-29 16:45 | Meeting (Whole Team) | 1 | team meeting with prof | team meeting wk4 | 2017-03-29
2017-03-29 16:45 | Nayem Alam | 1 | Worked on gantt chart, checklist for the week and checklist for the demo, and checklist for the poster | project management wk5 | 2017-03-29
2017-04-01 12:46 | Nayem Alam | 3 | working on the poster | designing the poster | 2017-04-01
2017-04-01 14:10 | Romain Nith | 5 | Generate LDD Files of final design and previous versions |  | 2017-03-31
2017-04-01 15:49 | Nayem Alam | 2 | still working on poster [almost done] | poster final design | 2017-04-01
2017-04-01 19:16 | Romain Nith | 3 | CAD Mark I, II and III LDD |  | 2017-04-01
2017-04-02 02:31 | Nayem Alam | 2 | almost finishing up poster | poster design final | 2017-04-02
2017-04-02 12:58 | Nayem Alam | 3 | almost done poster, one more thing left | poster design final | 2017-04-02
2017-04-02 19:04 | Rami Djema | 6 | Navigation! |  | 2017-03-27
2017-04-02 19:05 | Rami Djema | 6 | Navigation |  | 2017-04-02
2017-04-02 19:49 | Philippe Papineau | 4 | Finish documentation |  | 2017-04-02
2017-04-02 23:24 | Julien Courbebaisse | 7 | shooter implemented |  | 2017-04-02
2017-04-02 23:25 | Julien Courbebaisse | 3 | shooter documentation |  | 2017-04-02
2017-04-02 23:25 | Romain Nith | 3 | launcher design and testing |  | 2017-04-02
2017-04-03 11:36 | Philippe Papineau, Nayem Alam | 1 | team meeting | team meeting wk6 | 2017-04-03
2017-04-03 13:02 | Ali Sharif | 8 | Software Documentation |  | 2017-04-01
2017-04-03 14:15 | Nayem Alam | 2 | work on logistics | project management wk6 | 2017-04-03
2017-04-03 16:47 | Rami Djema | 2 | tested all modules and worked on results files | final integration testing | 2017-04-04
2017-04-03 17:04 | Julien Courbebaisse | 4 | review of software codes + testing | integration testing | 2017-04-04
2017-03-21 15:12 | Julien Courbebaisse | 4 | Software documentation |  | 2017-03-20
2017-03-21 15:14 | Julien Courbebaisse | 4 | Interface implementation and help with crossbow design |  | 2017-03-18

## Global Time Log
**Note: Please Write your hours in conventional format (i.e. 30 min = 0.5, 1hr = 1, 1h30 =1.5 ...)
Budget
| Week | 1 | 2 | 3 | 4 | 5 | 6 | Total | Overtime (During Break)
54hrs MAX per team member!
Nayem Alam | *Project Manager | 4 | 2 | 5 | 3 | 5 | 7 | 26 | 2
| Documentation | 4 | 2 | 2 |  | 1 |  | 9 |  | Management = Meetings
| Management | 2 | 2.5 | 3 | 2 | 5 | 1 | 15.5
| Hardware |  |  | 1 |  |  |  | 1
| Software | [6 empty] | 0 |  |  | Total Hours per member
| Testing | [6 empty] | 0 |  |  | Nayem | 54.5
| Other |  |  |  |  | 3 |  | 3 |  |  | Philippe | 57.5
[11 empty] | Ali | 54
Philippe Papineau | *Documentation | 2 |  |  | 10 | 6 | 4 | 22 | 2 |  | Rami | 54
| Hardware |  |  | 2 | 7 |  |  | 9 | 9 |  | Romain | 57
| Management | 2.5 | 4.5 | 3 | 2 | 4 | 1 | 17 |  |  | Julien | 54.5
| Software | [6 empty] | 0
| Testing |  | 5 |  |  |  |  | 5
| Other | 1.5 |  |  |  | 3 |  | 4.5
Ali Sharif | *Software |  |  | 5 | 7 | 7 | 6 | 25
| Testing |  | 1 | 2 | 6 |  |  | 9
| Management | 2.5 | 4.5 | 3 | 1 | 4 |  | 15
| Hardware |  |  | 4 |  |  |  | 4
| Documentation |  | 1 |  |  |  |  | 1 | 1
| Other | [6 empty] | 0
Rami Djema | *Software |  | 1 |  | 12 | 12 | 10 | 35
| Management | 2.5 | 2.5 | 2 | 1 | 4 |  | 12
| Documentation | [5 empty] | 2 | 2
| Hardware |  |  | 1 |  |  |  | 1
| Testing |  |  |  | 4 |  |  | 4
| Other | [6 empty] | 0
Romain Nith | *Hardware |  | 4 | 4 | 8 | 8 | 5 | 29
| Management | 2.5 | 4.5 | 2 | 1 | 4 |  | 14
| Documentation |  | 1 | 2 |  | 5 | 3 | 11
| Software | [6 empty] | 0
| Testing | [5 empty] | 3 | 3
| Other | [6 empty] | 0
Julien Courbebaisse | *Software |  | 2 | 3 | 6 | 4 | 7 | 22
| Management | 2 | 2.5 | 2 | 1 | 4 |  | 11.5
| Documentation |  | 1 |  | 4 | 2 | 3 | 10
| Hardware |  |  | 1 | 4 |  |  | 5
| Testing |  |  |  | 2 |  | 4 | 6
| Other | [6 empty] | 0
[9 empty] | 14 | Total Overtime Hours
TOTAL BUDGET | Week | 1 | 2 | 3 | 4 | 5 | 6 | TOTAL
| Hardware | 0 | 4 | 13 | 19 | 8 | 5 | 49
| Software | 0 | 3 | 8 | 25 | 23 | 23 | 82
| Documentation | 6 | 5 | 4 | 14 | 14 | 12 | 55
| Testing | 0 | 6 | 2 | 12 | 0 | 7 | 27
| Management | 14 | 21 | 15 | 8 | 25 | 2 | 85
| Other | 1.5 | 0 | 0 | 0 | 6 | 0 | 7.5
| Project Management | 4 | 2 | 5 | 3 | 5 | 7 | 26
[8 empty] | 331.5 | Total