## Sheet1
**Note: Please Write your hours in conventional format (i.e. 30 min = 0.5, 1hr = 1, 1h30 =1.5 ...)
Week | [7 empty] | Budget
1 | Feb20-24 |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | Total | Overtime (During Break)
2 | Mar6-10 | [10 empty] | 54hrs MAX per team member!
3 | Mar13-17 | Nayem Alam | *Project Manager | 4 | 2 | 5 | 3 | 5 | 7 | 26 | 2
4 | Mar20-24 |  | Documentation | 4 | 2 | 2 |  | 1 |  | 9 |  | Management = Meetings
5 | Mar27-31 |  | Management | 2 | 2.5 | 3 | 2 | 5 | 1 | 15.5
|  |  | Hardware | [6 empty] | 1 | bar: 3
|  |  | Software | [6 empty] | 0 |  |  | Total Hours per member
|  |  | Testing | [6 empty] | 0 |  |  | Nayem | 54.5
|  |  | Other | Budget 5: 3 | 3 |  |  | Philippe | 57.5
[13 empty] | Ali | 54
|  | Philippe Papineau | *Documentation | 2 |  |  | 10 | 6 | 4 | 22 | 2 |  | Rami | 54
|  |  | Hardware | 3: 2; 4: 7 | 9 | 9 |  | Romain | 57
|  |  | Management | 2.5 | 4.5 | 3 | 2 | 4 | 1 | 17 |  |  | Julien | 54.5
|  |  | Software | [6 empty] | 0
|  |  | Testing | 2: 5 | 5
|  |  | Other | 1: 1.5; Budget 5: 3 | 4.5
|  | Ali Sharif | *Software |  |  | 5 | 7 | 7 | 6 | 25
|  |  | Testing | 2: 1; 3: 2; 4: 6 | 9
|  |  | Management | 2.5 | 4.5 | 3 | 1 | 4 |  | 15
|  |  | Hardware | 3: 4 | 4
|  |  | Documentation | [6 empty] | 1 | 1 | bar: 2
|  |  | Other | [6 empty] | 0
|  | Rami Djema | *Software |  | 1 |  | 12 | 12 | 10 | 35
|  |  | Management | 2.5 | 2.5 | 2 | 1 | 4 |  | 12
|  |  | Documentation | Budget 6: 2 | 2
|  |  | Hardware | [6 empty] | 1 | bar: 3
|  |  | Testing | 4: 4 | 4
|  |  | Other | [6 empty] | 0
|  | Romain Nith | *Hardware |  | 4 | 4 | 8 | 8 | 5 | 29
|  |  | Management | 2.5 | 4.5 | 2 | 1 | 4 |  | 14
|  |  | Documentation |  | 1 | 2 |  | 5 | 3 | 11
|  |  | Software | [6 empty] | 0
|  |  | Testing | Budget 6: 3 | 3
|  |  | Other | [6 empty] | 0
|  | Julien Courbebaisse | *Software |  | 2 | 3 | 6 | 4 | 7 | 22
|  |  | Management | 2 | 2.5 | 2 | 1 | 4 |  | 11.5
|  |  | Documentation |  | 1 |  | 4 | 2 | 3 | 10
|  |  | Hardware | 3: 1; 4: 4 | 5
|  |  | Testing | 4: 2; Budget 6: 4 | 6
|  |  | Other | [6 empty] | 0
[11 empty] | 14 | Total Overtime Hours
|  | TOTAL BUDGET | Week | 1 | 2 | 3 | 4 | 5 | 6 | TOTAL
|  |  | Hardware | 0 | 4 | 13 | 19 | 8 | 5 | 49
|  |  | Software | 0 | 3 | 8 | 25 | 23 | 23 | 82
|  |  | Documentation | 6 | 5 | 4 | 14 | 14 | 12 | 55
|  |  | Testing | 0 | 6 | 2 | 12 | 0 | 7 | 27
|  |  | Management | 14 | 21 | 15 | 8 | 25 | 2 | 85
|  |  | Other | 1.5 | 0 | 0 | 0 | 6 | 0 | 7.5
|  |  | Project Management | 4 | 2 | 5 | 3 | 5 | 7 | 26
[10 empty] | 331.5 | Total